## Sheet1
Project Name | My Clinic
Created By | Faneshwar Gite
Creation Date | 2024-11-19
Bug Report
Bug ID | Priority | Description/Bug Summaey | Pre-requisities | Bug Steps | Potential Bug | Expected Result | Actual Result | Status | Test Excuted By
BUG-001 | Critical | OTP not received during login | Patient is registered in the system | 1. Go to login screen. 2. Enter phone number. 3. Click on "Send OTP". | OTP functionality failure (Network issue/Server issue) | OTP should be sent to the registered phone number. | OTP is not received after 2 minutes. | Open | Faneshwar Gite
BUG-002 | High | Appointment booking page not loading correctly | Patient is logged in | 1. Log in as a patient. 2. Go to "Book Appointment" page. 3. Wait for page to load. | Page load issue | Appointment page should load with available slots. | The page takes too long to load or shows a blank screen. | Open | Faneshwar Gite
BUG-003 | Low | Patient cannot cancel booked appointment | Patient has a scheduled appointment | 1. Log in as a patient. 2. Go to "My Appointments" page. 3. Try to cancel an appointment. | Button not responding | The appointment should be cancelled when the button is clicked. | The "Cancel Appointment" button is unresponsive. | Resolved | Faneshwar Gite
BUG-004 | Low | Incorrect slot availability displayed | Receptionist has configured slots | 1. Log in as a patient. 2. View available slots. 3. Select a slot. | Incorrect data | Available slots should be accurate and reflect the doctor's actual availability. | The available slot shown is already booked. | Open | Faneshwar Gite
BUG-005 | High | OTP for login works intermittently | Patient is registered and phone number is correct | 1. Log in as a patient. 2. Enter the phone number. 3. Receive OTP and enter it. | OTP generation issue (Server issue) | OTP should be generated and sent every time. | OTP fails to be received intermittently. | In Progress | Faneshwar Gite
BUG-006 | Critical | Receptionist cannot add new appointment slots for the week | Receptionist is logged in | 1. Log in as receptionist. 2. Try adding new appointment slots for the week. | Slot addition not saving | The new slots should be saved and visible to patients. | The newly added slots do not appear on the system. | Open | Faneshwar Gite
BUG-007 | High | SMS notification not sent after appointment booking | Patient has booked an appointment | 1. Book an appointment. 2. Wait for SMS notification. | SMS failure | Patient should receive an SMS confirmation after booking. | No SMS confirmation received. | Open | Faneshwar Gite
BUG-008 | Low | Receptionist cannot confirm appointments for patients | Receptionist has logged in | 1. Log in as receptionist. 2. Go to "View Appointments". 3. Try confirming a booking. | Button not responding | The confirmation button should work and confirm the appointment. | The "Confirm" button does not work. | In Progress | Faneshwar Gite